## User Stories
Story No | Menu | Feature | Request Name | User Story | Acceptance Criteria | Sprint Number | Story Points | Story ID | Priority | Notes | Approved by Client? | Questions | Owner | Developer | Dev Status | QA Status | Is it require Custimization
| Service Catalog |  | Service Catalog | As a Help Center Agent I need be able access the Service Catalog so that I can add items to the service catalog | Given that I am a Help Center agent I should be able to do the following 1. While in an account have the ability to select a "New Interaction Button" that allows me to access the service catalog 2. See a list of available categories and items that can be added to the service catalog | Sprint 1 | 1 | STR-001 | High | May need additional stories - Need all the flows |  |  | David |  | Dev Completed | QA Pass
STR-SP1-001 | Service Catalog |  | Service Catalog | As a Help Center Agent I should be able to Access Service Catalog After Clicking Validate on the customer validation module | Given that I am a Help Center agent I should be able to do the following 1. Access to the Customer Validation Module 2. "Validate" button within the Customer Validation Module that is visible and accesible 3. Be redirected the Service Catalog after a successful validation | Backlog TBD |  | STR-002 |  | Not doing this sprint
| Service Catalog |  | Service Catalog | Story to build out all of the categories in the shopping catalog
| Service Catalog |  | Service Catalog | As a Help Center Agent I need be able to search the Service Catalog so that I can add items to the service catalog to create a case | Given that I am a Help Center agent I should be able to do the following 1.Utilize a search mechanism with in the service catalog 2. left side section or panel on the screen where actions from the catalog can be selected. 3. When typing in characters to search real time results should appear narrowing down the selection 4. On the Right side of screen what should only be displayed are filtered results and that match only to the categories I have selected | Sprint 1 | 1 | STR-003 | High |  |  |  | David |  | Dev Completed | QA Pass
| Service Catalog |  | `!rTSYDUFRGTIYHLO;/.=- | As a Help Center Agent I need be to have the selected action(s) indicated as a selection on the left side of the screen so that an agent knows what has been added from the catalog | Given that I am a Help Center agent I should be able to do the following: 1. When I select an action from the catalog, it is visually indicated as being selected on the left side of the screen. 2. The selected action should remain a match on the left side until there is no longer a match 3. Ability to select another action from the catalog | Sprint 1 | 1 | STR-004 | High |  |  |  | David |  | Dev completed | QA Pass
STR-SP1-002 | Customer Validation |  | Customer Validation | As a Help Center Agent I need to be able to search records based on select criteria, including "Account Name", and specified encrypted fields, in order to retrieve accurate customer information | Given that I am a Help Center agent I should be able to do the following 1. Use a customers Account Name" as searchable criteria 2. return results matching the search criteria and partial matches 3. Sensitive data should remain encrypted throughout search process | Backlog TBD |  | STR-007 | High
STR-SP2-003 | imk jiuu y hfc |  | ubhi | As a Help Center Agent I need be able to have a Request Intake screen appear when I submit a case so that I can enter details about the case | Given that I am a Help Center agent I should be able to do the following: 1. The ability to click the create button to create a case from account page with the service catalog 2. For each agent action selected one parent case created and sudsequent child cases created 3. Ability to action a case clicking the start button on request intake screen 4. Ability to click Start and action the case from parent case 5. Have a success message confirming the submission of a child case | Sprint 1 | 2 | STR-008 | High |  |  |  | David |  | Dev completed | QA Pass
STR-SP2-004 | Service Catalog |  | Service Catalog | As a Help Center Agent I need be able access the Service Catalog from an account record so that I can link a case to account directly | Given that I am a Help Center agent I should be able to do the following 1. Have a link or button I can click on an account record to access the service catalog 2. Select an item while on a Salesforce account record 3. Have parent and child cases appear on the account in a case history tab | Sprint 1 | 1 | STR-010 | High | Need Client Input |  | Do we want a button or link on the account Page? Should it be on a related list? What Fields should we have displayed in the case history tab? | David |  | Dev completed | QA Pass
| Service Catalog |  | Service Catalog | As a Help Center Agent I need be able access the Service Catalog from Parent Case record so that I can add a child case to the record | Given that I am a Help Center Agent I should be able to do the following: 1. Open a Parent Case record in Salesforce and be able to access the service catalog using a button or link 2. Click the "Add More Requests" button and have service catalog displayed within the Request Intake tab 3. Have a List of available services of service catalog items that can be added as child cases. 4. Ability to select select multiple items from the Service Catalog to add as child cases to the current Parent Case record. 5. Once you click create button, the items/categories will be created as child cases | Sprint 1 | 2 | STR-011 | High |  |  |  | David |  | Dev completed | QA Pass
| Request Intake |  | Password Reset | As a Help Center Agent I need to be able to retrieve a temporary password from Genie when I click a button so that a user can log in with their temporary password | Given that I am a Help Center Agent I should be able to do the following: 1. Enter the User ID in a free text field 2. When the button is clicked, the mock page with mock(Dummy) username and password appears 3. Customer User ID displays as read-only 4. Temporary Password displays as read-only ***A Mock Service will be used to make the call to Genie since the Mulesoft solution isn't built yet*** | Sprint 2 | 5 | STR-012 | High | As customer User name is going to be auto populated and read only in future, changing the customer user name to read only is not implemented as part of this story. |  | Mock Service will be used - Will revisit this story once we get the Mock Service from client |  |  | Dev Completed |  | Yes
Connection To Mock service story
STR-SP2-005 | Request Intake |  | Password Reset | As a Help Center Agent I need to be able to access a flow that initiates a password reset so that the end user can be provided a temporary password (Read by agent) | Given that I am a help center agent I should have the following 1. A Page with the following Sections: a. Overview -Guidance text (Refer to Mock-Up) b. Reset Password - Reset Password section has a Text field for Customer ID c. Reset Info - Picklist Field for Reason, if Other is selected the details field (text) should be required 2. A finish button that closes the case confirming the completion of password reset request 3. A Success message confirming that password reset has been completed 4. By Default the sections should be expanded but each section is collapsable by selecting the arrow icon 5. Child task should be automatically closed upon finish | Sprint 1 | 5 | STR-013 | High | Password Request is one of the most common service requests - Need Client Input |  | Should Reason be required? What other picklist options should be for reason? Check about Password Requirements with Jordan and Morgan Stanley (Hyperlink not in scope) Do we have any verbage for the success message What is customer User Name field on Account Page that need to autopopulate | David |  | Dev Completed | QAPass
STR-SP1-003 | Agent Workflows |  | Password Reset | As System I need to be able to have a integration with Genie so the APi isnt blocked on the Password Reset requests | As a system I should have the following: 1. Ability to send Password Reset requests to Genie using the integrated API. | Backlog TBD |  | STR-014 |  | Backlog story once true service is built via Mulesoft
STR-SP2-007 | Request Intake |  | IVR Reset | As a Help Center Agent I need to be able to access a flow that iniates a IVR Pin reset for an authenticated user so that they can be sent a link to reset their IVR pin | Given that I am a help center agent I should have the following 1. Click through a IVR Pin Flow with the following sections: a. Overview -Guidance Text b. IVR Pin reset -Reset IVR section has a Text field for Customer Username - Read only New IVR Pin Field c. Reset Info 2. A button that confirms the submission of the IVR Pin reset request 3. A Success message confirming that IVR reset has been submitted successfully 4. By Default the sections should be expanded but each section is collapsable by selecting the arrow icon 5. Child task should be automatically closed upon submit | Sprint 2 |  | STR-015 |  | Need Client Input |  | Are there any additional Picklist fields we need to add? How should the screen Look?
| Request Intake |  |  | As a Help center agent I need to be able to have a parent case automatically close once all the child cases are closed so that a case can be complete | Given that I am a help center agent I should have the following: 1. Automatic closure of parent case once all child cases are closed | Sprint 2 |  | STR-016
| Request Intake |  | IVR Reset | As a Help Center Agent I need to be able to retrieve a temporary IVR Pin from Genie when I click a button so that a user reset | Given that I am a Help Center Agent I should have the following: 1.Have a button or link that allows me to initiate a temporary IVR Pin from Genie 2. When the button is clicked, it should trigger a request to Genie to generate a temporary IVR Pin for a specified user 3. The option to select the user who the temporary password should be sent to ***Mock Service used for this retreival initally*** | Sprint 2 |  | STR-017
STR-SP1-004 | Request Intake |  | IVR Reset | As Help center agent I need to be able to have a integration with Genie so the APi isnt blocked on the IVR Reset requests | As a system I should have the following: 1. Ability to send IVR Reset requests to Genie using the integrated API. | Backlog TBD |  |  |  | Backlog story - will update once real service is built
STR-SP1-005 | Request Intake |  | Change Login ID | As a Help Center Agent I need to be able to access a flow that iniates a Change Login ID reset for an authenticated user so that they can be sent a link to reset their User ID | Given that I am a help center agent I should have the following 1. Add a flow to the shopping the cart that is related to changing a user ID 2. Click through a Change Login ID Flow with the following: | Backlog TBD |  |  |  | Need Client Input |  | Are there any additional Picklist fields we need to add? How should the screen Look?
STR-SP1-006 | Request Intake |  | Security Questions | As a Help Center Agent I need to be able to access a flow that iniates a Change Security Question reset for an authenticated user so that they can be sent a link to change their security questions | Given that I am a help center agent I should have the following 1. Add a flow to the shopping the cart that is related to changing a user's security question 2. Click through a Change Security Question Flow with the following: | Backlog TBD |  |  |  | Need Client Input |  | Are there any additional Picklist fields we need to add? How should the screen Look?
|  |  |  | Financial flow permission |  | Sprint 2
| Deployment |  |  | Regression Tasks 5 Profiles |  | Sprint 2
| Deployment |  |  | I need be able to deploy to Morgan Stanley Enviornment | Deployment Placeholder | Sprint 2
| Service Catalog |  | Service Catalog | As a Help Center Agent I need to be able to Removing Items from the service catalog using the trash icon | Given that I am a help center agent 1. The trash icon should be visible for each item in the service catalog that can be removed. 2. Clicking the icon should be immediately removed from the service catalog. | Sprint 1 | 1 | STR-005 |  | Do we need to create a persona / profile for the help center agent ? |  |  |  |  | Dev Completed | QA Pass
| Service Catalog |  | Service Catalog | As a Help Center Agent I need to be able Remove an item from the service catalog by clicking X from cart | 1. Each selected item should have a X icon should appear next to them 2. When I click the X button next to an item it should be de-selected and no longer in cart | Sprint 1 | 1 | STR-006 | [6 empty] | Dev Completed | QA Pass
|  |  | Request Intake | As a Help Center Agent I need to have a default case status set to In Progress for a parent case and then "In progress" for all cases, parent and child once the case is started | Given that I am a help center agent I should have the following 1. The parent case is should be in "In Progress" Status once a case starts being actioned 2. When a Child case is created status defaulted to New . | Sprint 1 | 3 |  |  | Parent is in-progress status when agent action is selected ---- Child Caseis in the new status . Do you want to change to "In Progress" |  | Dev Team Notes: Parent will be In progress. Child will be in 'New' Status until we click on the start button. Do we need change all inprogress? |  | Shana | Dev Completed | QA Pass retest done
|  |  | Request Intake | As a Help Center Agent when I click the Save Button actioning a case the case should not be submitted and go draft / pending Status | Given that I am a help center agent I should have the following 1. When I click the save button when actioning a case the case should be set to a status of "Pending" and should not be marked as closed 2. Parent Case Should be remain In-progress (If has more than one Child case and other child case has not closed ) 3. Parent case should get closed , when all child cases are closed . 4. if the parent case has only one child case then parent case shoud close upon closing the child case | Sprint 1 | 2 |  |  |  |  | Change from Pennding to Draft Dev Team Notes: Status values for Parent and Child Cases need to finalized | Shana Parvin |  | Dev Completed | QA Pass
STR-SP2-008 |  |  | Request Intake | As a Help Center Agent I need have cases set as a default priority set of "Medium" for both parent and Child | Given that I am a help center agent I should have the following 1. When a case is created the default priority of the case should be set to "Medium" 2. When a case is created the default Case Orgin of the case should be set to "Phone" | Sprint 1 | 1 |  |  | Applicable only for Parent case |  | Dev Team Notes : 1. should the priority field of case set to "Medium" ? re-verify priority set to medium and Origin set to Phone |  | Aishwarya | Dev Completed | QA Pass
|  |  | Request Intake | As a Help Center Agent I need have cases set as a default subject set for both parent and child objects | Given that I am a help center agent I should have the following 1. Parent Case : Case Origin + Account Name 2. When a Child case is created the default subject should include Case Type + Account Name eg(Password Reset - David ) | Sprint 1 | 3 |  |  | Need Client Input If User selected more than one case Type , what should be the parent case type |  |  |  | Dinesh R | Dev Completed | QA Pass | yes, currently it coming call - Account name . Need to change Agent Action - Account Name
STR-SP2-009 |  |  | Request Intake | As a Help Center Agent I need have cases set as a default case type as the agent action requested (Password reset etc)" for cases | Given that I am a help center agent I should have the following 1. When a case is created the default Parent Case Type should be set to "Interaction" 2. The Child case Type should be the action name eg. password reset | Sprint 1 | 1 |  |  | Need Client Input Need to check the Case Status |  | Dev Team Notes : Re-verify Case Type on Child Case |  | Lalitha | Dev Completed | QA Pass
STR-SP2-010 |  |  | Request Intake | As a Help Center Agent I need to have certain fields displayed on the Parent and Child Highlight Panel on a case | Given that I am a help center agent I should have the following 1. On A Parent Case Record the following fields should appear on the highlight panel a. Case Number a. Account Name b. Case Origin c. Created Date e.Priority f.Case Owner h.Case Type --------------------------------------- 1. On A Child Case Record the following fields should appear on the highlight panel a. Case Number a. Account Name b. Parent Case Number c. Created Date e.Priority f.Case Owner h.Case Type | Sprint 1 | 3 |  |  | Need Client Input Can we include the parent case on the child record high light pannel Subject instead of case type or orgin |  |  |  | Lalitha | Dev Completed | QA Pass
|  |  | Request Intake | As a Help Center Agent I need a Path Lifecycle on a case record for the parent and Child Chase | Given that I am a help center agent I should have a Path lifecylce with Chevrons for the following Statues: 1. New 2. In Progress 3. Pending 4. Closed | Sprint 1 | 3 |  |  |  |  | Dev Team Notes: Status values for Parent and Child Cases need to finalized |  | Aishwarya | Dev Completed | QA Pass
STR-SP2-011 | Service Catalog |  | Request Intake | As Help Center Agent I should have a Parent Case Page that captures so information so that child cases can be captured | Given that I am a help center agent I should have a Parent Case that captures the following information |  |  |  |  | Need Client Input
STR-SP2-012 | Service Catalog |  | Request Intake | As a Help Center Agent I need have a lightning page with specific components | Given that I am a help center agent I should have a Lighting Page with the following Components a. Tasks b. Activity c. Chatter Feed / Case Feed d. Email Component e. Related Contact | Sprint 1 | 3 |  |  |  |  | Dev Team Notes : Need to check the chatter post not showing up on the page |  | Sahana | Dev Completed | QA Pass
STR-SP2-013 | Service Catalog |  | Service Catalog | As a Help Center Agent I need be able access the Service Catalog from a contact record so that I can link a case to Case directly | Given that I am a Help Center agent I should be able to do the following 1. Have a link or button I can click on an Contact record to access the service catalog 2. Select an item while on a existing Contact record 3. Have parent and child cases appear on theContact in a case history tab | Sprint 1 | 5 | STR-010 |  | STORY Not needed |  | Do we want a button or link on the Contact Page? Should it be on a related list? What Fields should we have displayed in the case history tab? | David | Sahana | Cancelled
STR-SP2-014 | Package Clean-Up |  |  | I need to be able to have a package clean up | Package Clean Up | Sprint 1 | 5
STR-SP1-007 | Knowledge |  |  | I need to be able to Link Overview Section to a Salesforce Knowledge Article | Given that I am a help center agent I need to be able to do the following 1. Access a knowledge article | Backlog |  |  |  | Not Implementing
STR-SP2-016 | Account Mangement
Note on B2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: FF shouldn't be the feature. Let's split into three features: Service Catalog, Request Intake, and Agent Workflows
Note on D2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Let's have stories for (1) the ability to search for these (and specify how the search works; # chars required for the search, live vs. pressing enter, etc.), (2) when the action is clicked it shows in the catalog on left side and is highlighted, and (3) when user clicks submit the cases are created for the select actions and the appropriate request intake form appears
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Jordan Kunz (US)
Note on E9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Jordan Kunz (US) Reply: Let's also have a story for the ability to do this from parent case. Reply: Done @Jordan Kunz (US)
Note on D13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Let's add another story for the ability to retrieve the temp password from Genie service when user clicks the appropriate button. Add another story doing the same for IVR PIN reset
Note on E13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Jordan Kunz (US) Reply: If we're not doing any check that a user is authenticated, let's remove that from the description
Note on F13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Let's keep the ability to add something to the shopping cart and the actual workflow separate Reply: Let's specify what the click through is like; what do we click on parent case to initiate, what appears on the screen, what user enters, etc.
Note on K13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @David Hodges (US) Draft a success Message for Password reset flow
Note on E15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @David Hodges (US) Let's run a spellcheck. Seeing a number of typos
Note on F18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @David Hodges (US) For system related stories,, can we write ACs in way so that Testing team can follow and test accordingly
Note on E35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Jordan Kunz (US) Reply: Let's also have a story for the ability to do this from parent case. Reply: Done @Jordan Kunz (US)

## Sprint 2
Story No | Menu | Feature | Request Name | User Story | Acceptance Criteria | Sprint Number | Story Points | Story ID | Priority | Notes | Approved by Client? | Questions | Owner | Developer | Dev Status | QA Status | Is it require Custimization
| Service Catalog |  | Service Catalog | As a Help Center Agent I need be able access the Service Catalog so that I can add items to the service catalog | Given that I am a Help Center agent I should be able to do the following 1. While in an account have the ability to select a "New Interaction Button" that allows me to access the service catalog 2. See a list of available categories and items that can be added to the service catalog | Sprint 1 | 1 | STR-001 | High | May need additional stories - Need all the flows |  |  | David |  | Dev Completed
| Service Catalog |  | Service Catalog | As a Help Center Agent I should be able to Access Service Catalog After Clicking Validate on the customer validation module | Given that I am a Help Center agent I should be able to do the following 1. Access to the Customer Validation Module 2. "Validate" button within the Customer Validation Module that is visible and accesible 3. Be redirected the Service Catalog after a successful validation | Backlog TBD |  | STR-002 |  | Not doing this sprint
| Service Catalog |  | Service Catalog | Story to build out all of the categories in the shopping catalog
| Service Catalog |  | Service Catalog | As a Help Center Agent I need be able to search the Service Catalog so that I can add items to the service catalog to create a case | Given that I am a Help Center agent I should be able to do the following 1.Utilize a search mechanism with in the service catalog 2. left side section or panel on the screen where actions from the catalog can be selected. 3. When typing in characters to search real time results should appear narrowing down the selection 4. On the Right side of screen what should only be displayed are filtered results and that match only to the categories I have selected | Sprint 1 | 1 | STR-003 | High |  |  |  | David |  | Dev Completed
| Service Catalog |  | Service Catalog | As a Help Center Agent I need be to have the selected action(s) indicated as a selection on the left side of the screen so that an agent knows what has been added from the catalog | Given that I am a Help Center agent I should be able to do the following: 1. When I select an action from the catalog, it is visually indicated as being selected on the left side of the screen. 2. The selected action should remain a match on the left side until there is no longer a match 3. Ability to select another action from the catalog | Sprint 1 | 1 | STR-004 | High |  |  |  | David |  | Dev completed
| Customer Validation |  | Customer Validation | As a Help Center Agent I need to be able to search records based on select criteria, including "Account Name", and specified encrypted fields, in order to retrieve accurate customer information | Given that I am a Help Center agent I should be able to do the following 1. Use a customers Account Name" as searchable criteria 2. return results matching the search criteria and partial matches 3. Sensitive data should remain encrypted throughout search process | Backlog TBD |  | STR-007 | High
| Service Catalog |  | Service Catalog | As a Help Center Agent I need be able to have a Request Intake screen appear when I submit a case so that I can enter details about the case | Given that I am a Help Center agent I should be able to do the following: 1. The ability to click the create button to create a case from account page with the service catalog 2. For each agent action selected one parent case created and sudsequent child cases created 3. Ability to action a case clicking the start button on request intake screen 4. Ability to click Start and action the case from parent case 5. Have a success message confirming the submission of a child case | Sprint 1 | 2 | STR-008 | High |  |  |  | David |  | Dev completed
| Service Catalog |  | Service Catalog | As a Help Center Agent I need be able access the Service Catalog from an account record so that I can link a case to account directly | Given that I am a Help Center agent I should be able to do the following 1. Have a link or button I can click on an account record to access the service catalog 2. Select an item while on a Salesforce account record 3. Have parent and child cases appear on the account in a case history tab | Sprint 1 | 1 | STR-010 | High | Need Client Input |  | Do we want a button or link on the account Page? Should it be on a related list? What Fields should we have displayed in the case history tab? | David |  | Dev completed
| Service Catalog |  | Service Catalog | As a Help Center Agent I need be able access the Service Catalog from Parent Case record so that I can add a child case to the record | Given that I am a Help Center Agent I should be able to do the following: 1. Open a Parent Case record in Salesforce and be able to access the service catalog using a button or link 2. Click the "Add More Requests" button and have service catalog displayed within the Request Intake tab 3. Have a List of available services of service catalog items that can be added as child cases. 4. Ability to select select multiple items from the Service Catalog to add as child cases to the current Parent Case record. 5. Once you click create button, the items/categories will be created as child cases | Sprint 1 | 2 | STR-011 | High |  |  |  | David |  | Dev completed
STR-SP2-001 | Request Intake |  | Password Reset | As a Help Center Agent I need to be able to retrieve a temporary password from Genie when I click a button so that a user can log in with their temporary password | Given that I am a Help Center Agent I should be able to do the following: 1. Enter the User ID in a free text field 2. When the continue button is clicked, the mock page with (Dummy) password appears for the user Id 3. Customer User ID displays as read-only 4. Temporary Password displays as read-only ***A Mock Service will be used to make the call to Genie since the Mulesoft solution isn't built yet*** | Sprint 2 | 5 | STR-012 | High | We will develop User Interface |  | Mock Service will be used - Will revisit this story once we get the Mock Service from client |  | Sahana | Dev Completed | QA Pass re-test done | Yes | Re-Test
Connection To Mock service story
| Request Intake |  | Password Reset | As a Help Center Agent I need to be able to access a flow that initiates a password reset so that the end user can be provided a temporary password (Read by agent) | Given that I am a help center agent I should have the following 1. A Page with the following Sections: a. Overview -Guidance text (Refer to Mock-Up) b. Reset Password - Reset Password section has a Text field for Customer ID c. Reset Info - Picklist Field for Reason, if Other is selected the details field (text) should be required 2. A finish button that closes the case confirming the completion of password reset request 3. A Success message confirming that password reset has been completed 4. By Default the sections should be expanded but each section is collapsable by selecting the arrow icon 5. Child task should be automatically closed upon finish | Sprint 1 | 5 | STR-013 | High | Password Request is one of the most common service requests - Need Client Input |  | Should Reason be required? What other picklist options should be for reason? Check about Password Requirements with Jordan and Morgan Stanley (Hyperlink not in scope) Do we have any verbage for the success message What is customer User Name field on Account Page that need to autopopulate | David |  | Dev Completed
| Agent Workflows |  | Password Reset | As System I need to be able to have a integration with Genie so the APi isnt blocked on the Password Reset requests | As a system I should have the following: 1. Ability to send Password Reset requests to Genie using the integrated API. | Backlog TBD |  | STR-014 |  | Backlog story once true service is built via Mulesoft
STR-SP2-002 | Request Intake |  | IVR Reset | As a Help Center Agent I need to be able to access a flow that iniates a IVR Pin reset for an authenticated user so that they can be sent a link to reset their IVR pin |  | Sprint 2 | 5 | STR-015 |  | Need Client Input |  | Are there any additional Picklist fields we need to add? How should the screen Look? |  | Sahana | Dev Completed | QA Pass Re-test done | Re-test
STR-SP2-003 | Request Intake |  | Request Intake | As a Help center agent I need to be able to have a parent case automatically close once all the child cases are closed so that a case can be complete | Given that I am a help center agent I should have the following: 1. Automatic closure of parent case once all child cases are closed | Sprint 2 | 3 | STR-016 | [5 empty] | Aishwarya | Dev Completed | QA Pass
STR-SP2-004 | Request Intake |  | IVR Reset | As a Help Center Agent I need to be able to retrieve a temporary IVR Pin from Genie when I click the continue button so that a user can reset their pin | Given that I am a Help Center Agent I should have the following: 1.Have a button or link that allows me to initiate a temporary (Dummy) IVR Pin in Mock Page 2. When the button is clicked, it should trigger a request to Genie to generate a temporary IVR Pin for a specified user 3. The option to select the user who the temporary IVR Pin should be sent to ***Mock Service used for this retreival initally*** | Sprint 2 | 5 | STR-017 | [5 empty] | Sahana | Dev Completed | QA Pass | Test as Integration part removed
| Request Intake |  | IVR Reset | As Help center agent I need to be able to have a integration with Genie so the APi isnt blocked on the IVR Reset requests | As a system I should have the following: 1. Ability to send IVR Reset requests to Genie using the integrated API. | Backlog TBD |  |  |  | Backlog story - will update once real service is built
| Request Intake |  | Change Login ID | As a Help Center Agent I need to be able to access a flow that iniates a Change Login ID reset for an authenticated user so that they can be sent a link to reset their User ID | Given that I am a help center agent I should have the following 1. Add a flow to the shopping the cart that is related to changing a user ID 2. Click through a Change Login ID Flow with the following: | Backlog TBD |  |  |  | Need Client Input |  | Are there any additional Picklist fields we need to add? How should the screen Look?
| Request Intake |  | Security Questions | As a Help Center Agent I need to be able to access a flow that iniates a Change Security Question reset for an authenticated user so that they can be sent a link to change their security questions | Given that I am a help center agent I should have the following 1. Add a flow to the shopping the cart that is related to changing a user's security question 2. Click through a Change Security Question Flow with the following: | Backlog TBD |  |  |  | Need Client Input |  | Are there any additional Picklist fields we need to add? How should the screen Look?
STR-SP2-005 |  |  |  | As a Business User I need to have a Permission Set for Financial Flow access | Given that I am a Help Center Agent I should have the following 1. Access to one permission set that allows me to access financial flows 2. Any business user with this permission set should be able to access financial flows (Not profile specific who already have acces to service cloud record case, account, contact) | Sprint 2 | 3 | [6 empty] | Dinesh | Dev Completed | QA Pass
STR-SP2-006 | Deployment |  |  | As a tester I need to do Regression Tasks 5 Profiles | I should have Regression testing for the following 5 profiles provided by MS 1.CS-Communications 2.CS-Management 3.CS-Research and Resolution 4.CS-Techncial Support 5.CS-User | Sprint 2 | 5 | [7 empty] | Deployment pending
STR-SP2-007 | Deployment |  |  | I need be able to deploy to Morgan Stanley Enviornment | Deployment Placeholder | Sprint 2 | 5 | [6 empty] | Vishnu | Deployment pending
| Service Catalog |  | Service Catalog | As a Help Center Agent I need to be able to Removing Items from the service catalog using the trash icon | Given that I am a help center agent 1. The trash icon should be visible for each item in the service catalog that can be removed. 2. Clicking the icon should be immediately removed from the service catalog. | Sprint 3 | 1 | STR-005 |  | Do we need to create a persona / profile for the help center agent ? |  |  |  |  | Dev Completed
| Service Catalog |  | Service Catalog | As a Help Center Agent I need to be able Remove an item from the service catalog by clicking X from cart | 1. Each selected item should have a X icon should appear next to them 2. When I click the X button next to an item it should be de-selected and no longer in cart | Sprint 1 | 1 | STR-006 | [6 empty] | Dev Completed
|  |  | Request Intake | As a Help Center Agent I need to have a default case status set to In Progress for a parent case and then "In progress" for all cases, parent and child once the case is started | Given that I am a help center agent I should have the following 1. The parent case is should be in "In Progress" Status once a case starts being actioned 2. When a Child case is created status defaulted to New . | Sprint 1 | 3 |  |  | Parent is in-progress status when agent action is selected ---- Child Caseis in the new status . Do you want to change to "In Progress" |  | Dev Team Notes: Parent will be In progress. Child will be in 'New' Status until we click on the start button. Do we need change all inprogress? |  | Shana | Dev Completed
|  |  | Request Intake | As a Help Center Agent when I click the Save Button actioning a case the case should not be submitted and go draft / pending Status | Given that I am a help center agent I should have the following 1. When I click the save button when actioning a case the case should be set to a status of "Pending" and should not be marked as closed 2. Parent Case Should be remain In-progress (If has more than one Child case and other child case has not closed ) 3. Parent case should get closed , when all child cases are closed . 4. if the parent case has only one child case then parent case shoud close upon closing the child case | Sprint 1 | 2 |  |  |  |  | Change from Pennding to Draft Dev Team Notes: Status values for Parent and Child Cases need to finalized | Shana Parvin |  | Dev Completed
|  |  | Request Intake | As a Help Center Agent I need have cases set as a default priority set of "Medium" for both parent and Child | Given that I am a help center agent I should have the following 1. When a case is created the default priority of the case should be set to "Medium" 2. When a case is created the default Case Orgin of the case should be set to "Phone" | Sprint 1 | 1 |  |  | Applicable only for Parent case |  | Dev Team Notes : 1. should the priority field of case set to "Medium" ? re-verify priority set to medium and Origin set to Phone |  | Aishwarya | Dev Completed
|  |  | Request Intake | As a Help Center Agent I need have cases set as a default subject set for both parent and child objects | Given that I am a help center agent I should have the following 1. Parent Case : Case Origin + Account Name 2. When a Child case is created the default subject should include Case Type + Account Name eg(Password Reset - David ) | Sprint 1 | 3 |  |  | Need Client Input If User selected more than one case Type , what should be the parent case type |  |  |  | Dinesh R | Dev Completed |  | yes, currently it coming call - Account name . Need to change Agent Action - Account Name
|  |  | Request Intake | As a Help Center Agent I need have cases set as a default case type as the agent action requested (Password reset etc)" for cases | Given that I am a help center agent I should have the following 1. When a case is created the default Parent Case Type should be set to "Interaction" 2. The Child case Type should be the action name eg. password reset | Sprint 1 | 1 |  |  | Need Client Input Need to check the Case Status |  | Dev Team Notes : Re-verify Case Type on Child Case |  | Lalitha | Dev Completed
|  |  | Request Intake | As a Help Center Agent I need to have certain fields displayed on the Parent and Child Highlight Panel on a case | Given that I am a help center agent I should have the following 1. On A Parent Case Record the following fields should appear on the highlight panel a. Case Number a. Account Name b. Case Origin c. Created Date e.Priority f.Case Owner h.Case Type --------------------------------------- 1. On A Child Case Record the following fields should appear on the highlight panel a. Case Number a. Account Name b. Parent Case Number c. Created Date e.Priority f.Case Owner h.Case Type | Sprint 1 | 3 |  |  | Need Client Input Can we include the parent case on the child record high light pannel Subject instead of case type or orgin |  |  |  | Lalitha | Dev Completed
|  |  | Request Intake | As a Help Center Agent I need a Path Lifecycle on a case record for the parent and Child Chase | Given that I am a help center agent I should have a Path lifecylce with Chevrons for the following Statues: 1. New 2. In Progress 3. Pending 4. Closed | Sprint 1 | 3 |  |  |  |  | Dev Team Notes: Status values for Parent and Child Cases need to finalized |  | Aishwarya | Dev Completed
| Service Catalog |  | Request Intake | As Help Center Agent I should have a Parent Case Page that captures so information so that child cases can be captured | Given that I am a help center agent I should have a Parent Case that captures the following information | Sprint 1 |  |  |  | Need Client Input
| Service Catalog |  | Request Intake | As a Help Center Agent I need have a lightning page with specific components | Given that I am a help center agent I should have a Lighting Page with the following Components a. Tasks b. Activity c. Chatter Feed / Case Feed d. Email Component e. Related Contact | Sprint 1 | 3 |  |  |  |  | Dev Team Notes : Need to check the chatter post not showing up on the page |  | Sahana | Dev Completed
| Service Catalog |  | Service Catalog | As a Help Center Agent I need be able access the Service Catalog from a contact record so that I can link a case to Case directly | Given that I am a Help Center agent I should be able to do the following 1. Have a link or button I can click on an Contact record to access the service catalog 2. Select an item while on a existing Contact record 3. Have parent and child cases appear on theContact in a case history tab | Backlog | 5 | STR-010 |  | STORY Not needed |  | Do we want a button or link on the Contact Page? Should it be on a related list? What Fields should we have displayed in the case history tab? | David | Sahana | Cancelled
STR-SP2-008 | Package Clean-Up |  |  | I need to be able to have a package clean up | Package Clean Up | Sprint 2
| Account Mangement |  |  |  |  | Sprint 3
STR-SP2-009 | Service Catalog |  |  | I need to be able to have all Service Catalog Items built out so that I can access all service requests for a case | Given that i am a help center agent I need to have access to the following Service Catalog Items 1. Create all Categories from the Service Catalog 2. Create the issue type/Agent action for each Category in the catalog | Sprint 2 | 5 | [6 empty] | Lalitha | Dev Completed | QA Pass
STR-SP2-010 | Account Mangement |  | Account Update | As a Help Center Agent I need to be able to access a flow that iniates an Account Update for an authenticated user so that they can Update their account details | Given that i am a help center agent I need to have the following 1. Account information Section a. Account Name b. Account Number c. Account Type d. Tier Level e. Account Address f. Primary Phone g. Email Address 2. Account Comments a. Comments - Free Text Field (Text Area) | Sprint 2 | 3 | [6 empty] | Lalitha | Dev Completed | QA Pass re-test done | Re-test
| Account Mangement |  | Account Update | UX Placeholder for Account Update | UX Placeholder |  | 1
STR-SP2-011 | Account Mangement |  | Addres Change | As a Help Center Agent I need to be able to access a flow that initates a Address change so that a user can change their address in the system | Given that i am a help center agent I need to have the following 1. Account Information Section a. Account Name b. Account Number c. Account Type d. Tier Level e. Account Address f. Primary Phone g. Email Address 2. Address Change Section a. Comments - Text Area | Sprint 2 | 3 | [6 empty] | Lalitha | Dev Completed | QA Pass Re-test done | Re-test
STR-SP2-012 | Account Mangement |  | Address Change | UX Placeholder for Address Change | UX Placeholder | Sprint 2 | 1 | [6 empty] | Nitish | UX Completed | QA Pass | story has been updated
STR-SP2-013 | Account Mangement |  | Due To Death Issue | As a Help Center Agent I need to be able to access a flow that performs Due to Death issue | Given that i am a help center agent I need to have the following 1. Account Information Section a. Account Name b. Account Number c. Account Type d. Tier Level e. Account Address f. Primary Phone g. Email Address 2. Due to Death Issue Comments a. Comments - Text Field | Sprint 2 | 3 |  |  | May be customer validation model |  |  |  | Aishwarya | Dev Completed | QA Pass
STR-SP2-014 | Account Mangement |  | Due To Death Issue | UX Placeholder for Due to Death Issue | UX Placeholder | Sprint 2 | 1 | [6 empty] | Nitish | Dev Completed | QA Pass
STR-SP2-015 | Account Mangement |  | Missing Info Ap | As a Help Center Agent I need to be able to access to a flow that performs Missing Info - App | Given that i am a help center agent I need to have the following Given that i am a help center agent I need to have the following 1. Account Information Section a. Account Name b. Account Number c. Account Type d. Tier Level e. Account Address f. Primary Phone g. Email Address 2. Missing Info Comments a. Comments - Text Field | Sprint 2 | 3 | [6 empty] | Aishwarya | Dev Completed | QA Pass
STR-SP2-016 | Account Mangement |  | Missing Info App | UX Placeholder for Missing info-App | UX Placeholder | Sprint 2 | 1 | [6 empty] | Nitish | Dev Completed | QA Pass
| Internal Demo Feedback |  | Recommendations Section |  | Given that i am a help center agent I need to have the following OOTB functionality from FF package • Recommendations on left side section in Home Page When the Help center agent click on "Recommendations" , on right side differ
5
Note on B2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: FF shouldn't be the feature. Let's split into three features: Service Catalog, Request Intake, and Agent Workflows
Note on D2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Let's have stories for (1) the ability to search for these (and specify how the search works; # chars required for the search, live vs. pressing enter, etc.), (2) when the action is clicked it shows in the catalog on left side and is highlighted, and (3) when user clicks submit the cases are created for the select actions and the appropriate request intake form appears
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Jordan Kunz (US)
Note on E9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Jordan Kunz (US) Reply: Let's also have a story for the ability to do this from parent case. Reply: Done @Jordan Kunz (US)
Note on D13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Let's add another story for the ability to retrieve the temp password from Genie service when user clicks the appropriate button. Add another story doing the same for IVR PIN reset
Note on E13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Jordan Kunz (US) Reply: If we're not doing any check that a user is authenticated, let's remove that from the description
Note on F13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Let's keep the ability to add something to the shopping cart and the actual workflow separate Reply: Let's specify what the click through is like; what do we click on parent case to initiate, what appears on the screen, what user enters, etc.
Note on K13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @David Hodges (US) Draft a success Message for Password reset flow
Note on E15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @David Hodges (US) Let's run a spellcheck. Seeing a number of typos
Note on F17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @David Hodges (US) we are not building this AC3 as part of this story . we need more information to show are all user . Can you strick out and add this as new story on sprint 4 3. The option to select the user who the temporary IVR Pin should be sent to
Note on F18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @David Hodges (US) For system related stories,, can we write ACs in way so that Testing team can follow and test accordingly
Note on E35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Jordan Kunz (US) Reply: Let's also have a story for the ability to do this from parent case. Reply: Done @Jordan Kunz (US)

## Sprint 3
Story No | Menu | Feature | Request Name | User Story | Acceptance Criteria | Sprint Number | Story Points | Story ID | Priority | Notes | Approved by Client? | Questions | Owner | Developer | Dev Status | QA Status | Is it require Custimization
| Service Catalog |  | Service Catalog | As a Help Center Agent I need be able access the Service Catalog so that I can add items to the service catalog | Given that I am a Help Center agent I should be able to do the following 1. While in an account have the ability to select a "New Interaction Button" that allows me to access the service catalog 2. See a list of available categories and items that can be added to the service catalog | Sprint 1 | 1 | STR-001 | High | May need additional stories - Need all the flows |  |  | David |  | Dev Completed
| Service Catalog |  | Service Catalog | As a Help Center Agent I should be able to Access Service Catalog After Clicking Validate on the customer validation module | Given that I am a Help Center agent I should be able to do the following 1. Access to the Customer Validation Module 2. "Validate" button within the Customer Validation Module that is visible and accesible 3. Be redirected the Service Catalog after a successful validation | Backlog TBD |  | STR-002 |  | Not doing this sprint
| Service Catalog |  | Service Catalog | Story to build out all of the categories in the shopping catalog
| Service Catalog |  | Service Catalog | As a Help Center Agent I need be able to search the Service Catalog so that I can add items to the service catalog to create a case | Given that I am a Help Center agent I should be able to do the following 1.Utilize a search mechanism with in the service catalog 2. left side section or panel on the screen where actions from the catalog can be selected. 3. When typing in characters to search real time results should appear narrowing down the selection 4. On the Right side of screen what should only be displayed are filtered results and that match only to the categories I have selected | Sprint 1 | 1 | STR-003 | High |  |  |  | David |  | Dev Completed
| Service Catalog |  | Service Catalog | As a Help Center Agent I need be to have the selected action(s) indicated as a selection on the left side of the screen so that an agent knows what has been added from the catalog | Given that I am a Help Center agent I should be able to do the following: 1. When I select an action from the catalog, it is visually indicated as being selected on the left side of the screen. 2. The selected action should remain a match on the left side until there is no longer a match 3. Ability to select another action from the catalog | Sprint 1 | 1 | STR-004 | High |  |  |  | David |  | Dev completed
| Customer Validation |  | Customer Validation | As a Help Center Agent I need to be able to search records based on select criteria, including "Account Name", and specified encrypted fields, in order to retrieve accurate customer information | Given that I am a Help Center agent I should be able to do the following 1. Use a customers Account Name" as searchable criteria 2. return results matching the search criteria and partial matches 3. Sensitive data should remain encrypted throughout search process | Backlog TBD |  | STR-007 | High
| Service Catalog |  | Service Catalog | As a Help Center Agent I need be able to have a Request Intake screen appear when I submit a case so that I can enter details about the case | Given that I am a Help Center agent I should be able to do the following: 1. The ability to click the create button to create a case from account page with the service catalog 2. For each agent action selected one parent case created and sudsequent child cases created 3. Ability to action a case clicking the start button on request intake screen 4. Ability to click Start and action the case from parent case 5. Have a success message confirming the submission of a child case | Sprint 1 | 2 | STR-008 | High |  |  |  | David |  | Dev completed
| Service Catalog |  | Service Catalog | As a Help Center Agent I need be able access the Service Catalog from an account record so that I can link a case to account directly | Given that I am a Help Center agent I should be able to do the following 1. Have a link or button I can click on an account record to access the service catalog 2. Select an item while on a Salesforce account record 3. Have parent and child cases appear on the account in a case history tab | Sprint 1 | 1 | STR-010 | High | Need Client Input |  | Do we want a button or link on the account Page? Should it be on a related list? What Fields should we have displayed in the case history tab? | David |  | Dev completed
| Service Catalog |  | Service Catalog | As a Help Center Agent I need be able access the Service Catalog from Parent Case record so that I can add a child case to the record | Given that I am a Help Center Agent I should be able to do the following: 1. Open a Parent Case record in Salesforce and be able to access the service catalog using a button or link 2. Click the "Add More Requests" button and have service catalog displayed within the Request Intake tab 3. Have a List of available services of service catalog items that can be added as child cases. 4. Ability to select select multiple items from the Service Catalog to add as child cases to the current Parent Case record. 5. Once you click create button, the items/categories will be created as child cases | Sprint 1 | 2 | STR-011 | High |  |  |  | David |  | Dev completed
| Request Intake |  | Password Reset | As a Help Center Agent I need to be able to retrieve a temporary password from Genie when I click a button so that a user can log in with their temporary password | Given that I am a Help Center Agent I should be able to do the following: 1. Enter the User ID in a free text field 2. When the continue button is clicked, the mock page with (Dummy) password appears for the user Id 3. Customer User ID displays as read-only 4. Temporary Password displays as read-only ***A Mock Service will be used to make the call to Genie since the Mulesoft solution isn't built yet*** | Sprint 2 | 5 | STR-012 | High | We will develop User Interface |  | Mock Service will be used - Will revisit this story once we get the Mock Service from client |  | Sahana | Dev Completed | QA Pass re-test done | Yes | Re-Test
Connection To Mock service story
| Request Intake |  | Password Reset | As a Help Center Agent I need to be able to access a flow that initiates a password reset so that the end user can be provided a temporary password (Read by agent) | Given that I am a help center agent I should have the following 1. A Page with the following Sections: a. Overview -Guidance text (Refer to Mock-Up) b. Reset Password - Reset Password section has a Text field for Customer ID c. Reset Info - Picklist Field for Reason, if Other is selected the details field (text) should be required 2. A finish button that closes the case confirming the completion of password reset request 3. A Success message confirming that password reset has been completed 4. By Default the sections should be expanded but each section is collapsable by selecting the arrow icon 5. Child task should be automatically closed upon finish | Sprint 1 | 5 | STR-013 | High | Password Request is one of the most common service requests - Need Client Input |  | Should Reason be required? What other picklist options should be for reason? Check about Password Requirements with Jordan and Morgan Stanley (Hyperlink not in scope) Do we have any verbage for the success message What is customer User Name field on Account Page that need to autopopulate | David |  | Dev Completed
| Agent Workflows |  | Password Reset | As System I need to be able to have a integration with Genie so the APi isnt blocked on the Password Reset requests | As a system I should have the following: 1. Ability to send Password Reset requests to Genie using the integrated API. | Backlog TBD |  | STR-014 |  | Backlog story once true service is built via Mulesoft
| Request Intake |  | IVR Reset | As a Help Center Agent I need to be able to access a flow that iniates a IVR Pin reset for an authenticated user so that they can be sent a link to reset their IVR pin | Given that I am a help center agent I should have the following 1. Click through a IVR Pin Flow with the following sections: a. Overview -Guidance Text b.Reset IVR Pin -Reset IVR section has a Text field for Customer Username - Read only New IVR Pin Field c. Reset Info 2. A button that confirms the submission of the IVR Pin reset request 3. A Success message confirming that IVR reset has been submitted successfully 4. By Default the sections should be expanded but each section is collapsable by selecting the arrow icon 5. Child task should be automatically closed upon submit | Sprint 2 | 5 | STR-015 |  | Need Client Input |  | Are there any additional Picklist fields we need to add? How should the screen Look? |  | Sahana | Dev Completed | QA Pass Re-test done | Re-test
| Request Intake |  | Request Intake | As a Help center agent I need to be able to have a parent case automatically close once all the child cases are closed so that a case can be complete | Given that I am a help center agent I should have the following: 1. Automatic closure of parent case once all child cases are closed | Sprint 2 |  | STR-016 | [5 empty] | Aishwarya | Dev Completed | QA Pass
| Request Intake |  | IVR Reset | As a Help Center Agent I need to be able to retrieve a temporary IVR Pin from Genie when I click the continue button so that a user can reset their pin | Given that I am a Help Center Agent I should have the following: 1.Have a button or link that allows me to initiate a temporary (Dummy) IVR Pin in Mock Page 2. When the button is clicked, it should trigger a request to Genie to generate a temporary IVR Pin for a specified user 3. The option to select the user who the temporary IVR Pin should be sent to ***Mock Service used for this retreival initally*** | Sprint 2 | 5 | STR-017 | [5 empty] | Sahana | Dev Completed | QA Pass | Test as Integration part removed
| Request Intake |  | IVR Reset | As Help center agent I need to be able to have a integration with Genie so the APi isnt blocked on the IVR Reset requests | As a system I should have the following: 1. Ability to send IVR Reset requests to Genie using the integrated API. | Backlog TBD |  |  |  | Backlog story - will update once real service is built
| Request Intake |  | Change Login ID | As a Help Center Agent I need to be able to access a flow that iniates a Change Login ID reset for an authenticated user so that they can be sent a link to reset their User ID | Given that I am a help center agent I should have the following 1. Add a flow to the shopping the cart that is related to changing a user ID 2. Click through a Change Login ID Flow with the following: | Backlog TBD |  |  |  | Need Client Input |  | Are there any additional Picklist fields we need to add? How should the screen Look?
| Request Intake |  | Security Questions | As a Help Center Agent I need to be able to access a flow that iniates a Change Security Question reset for an authenticated user so that they can be sent a link to change their security questions | Given that I am a help center agent I should have the following 1. Add a flow to the shopping the cart that is related to changing a user's security question 2. Click through a Change Security Question Flow with the following: | Backlog TBD |  |  |  | Need Client Input |  | Are there any additional Picklist fields we need to add? How should the screen Look?
|  |  |  | As a Business User I need to have a Permission Set for Financial Flow access | Given that I am a Help Center Agent I should have the following 1. Access to one permission set that allows me to access financial flows 2. Any business user with this permission set should be able to access financial flows (Not profile specific) | Sprint 2 | 3 | [6 empty] | Dinesh | Dev Completed | QA Pass
| Deployment |  |  | As a tester I need to do Regression Tasks 5 Profiles | I should have Regression testing for the following 5 profiles provided by MS 1.CS-Communications 2.CS-Management 3.CS-Research and Resolution 4.CS-Techncial Support 5.CS-User | Sprint 2 | 5 | [7 empty] | Deployment pending
| Deployment |  |  | I need be able to deploy to Morgan Stanley Enviornment | Deployment Placeholder | Sprint 2 | 5 | [6 empty] | Vishnu | Deployment pending
| Service Catalog |  | Service Catalog | As a Help Center Agent I need to be able to Removing Items from the service catalog using the trash icon | Given that I am a help center agent 1. The trash icon should be visible for each item in the service catalog that can be removed. 2. Clicking the icon should be immediately removed from the service catalog. | Sprint 1 | 1 | STR-005 |  | Do we need to create a persona / profile for the help center agent ? |  |  |  |  | Dev Completed
| Service Catalog |  | Service Catalog | As a Help Center Agent I need to be able Remove an item from the service catalog by clicking X from cart | 1. Each selected item should have a X icon should appear next to them 2. When I click the X button next to an item it should be de-selected and no longer in cart | Sprint 1 | 1 | STR-006 | [6 empty] | Dev Completed
|  |  | Request Intake | As a Help Center Agent I need to have a default case status set to In Progress for a parent case and then "In progress" for all cases, parent and child once the case is started | Given that I am a help center agent I should have the following 1. The parent case is should be in "In Progress" Status once a case starts being actioned 2. When a Child case is created status defaulted to New . | Sprint 1 | 3 |  |  | Parent is in-progress status when agent action is selected ---- Child Caseis in the new status . Do you want to change to "In Progress" |  | Dev Team Notes: Parent will be In progress. Child will be in 'New' Status until we click on the start button. Do we need change all inprogress? |  | Shana | Dev Completed
|  |  | Request Intake | As a Help Center Agent when I click the Save Button actioning a case the case should not be submitted and go draft / pending Status | Given that I am a help center agent I should have the following 1. When I click the save button when actioning a case the case should be set to a status of "Pending" and should not be marked as closed 2. Parent Case Should be remain In-progress (If has more than one Child case and other child case has not closed ) 3. Parent case should get closed , when all child cases are closed . 4. if the parent case has only one child case then parent case shoud close upon closing the child case | Sprint 1 | 2 |  |  |  |  | Change from Pennding to Draft Dev Team Notes: Status values for Parent and Child Cases need to finalized | Shana Parvin |  | Dev Completed
|  |  | Request Intake | As a Help Center Agent I need have cases set as a default priority set of "Medium" for both parent and Child | Given that I am a help center agent I should have the following 1. When a case is created the default priority of the case should be set to "Medium" 2. When a case is created the default Case Orgin of the case should be set to "Phone" | Sprint 1 | 1 |  |  | Applicable only for Parent case |  | Dev Team Notes : 1. should the priority field of case set to "Medium" ? re-verify priority set to medium and Origin set to Phone |  | Aishwarya | Dev Completed
|  |  | Request Intake | As a Help Center Agent I need have cases set as a default subject set for both parent and child objects | Given that I am a help center agent I should have the following 1. Parent Case : Case Origin + Account Name 2. When a Child case is created the default subject should include Case Type + Account Name eg(Password Reset - David ) | Sprint 1 | 3 |  |  | Need Client Input If User selected more than one case Type , what should be the parent case type |  |  |  | Dinesh R | Dev Completed |  | yes, currently it coming call - Account name . Need to change Agent Action - Account Name
|  |  | Request Intake | As a Help Center Agent I need have cases set as a default case type as the agent action requested (Password reset etc)" for cases | Given that I am a help center agent I should have the following 1. When a case is created the default Parent Case Type should be set to "Interaction" 2. The Child case Type should be the action name eg. password reset | Sprint 1 | 1 |  |  | Need Client Input Need to check the Case Status |  | Dev Team Notes : Re-verify Case Type on Child Case |  | Lalitha | Dev Completed
|  |  | Request Intake | As a Help Center Agent I need to have certain fields displayed on the Parent and Child Highlight Panel on a case | Given that I am a help center agent I should have the following 1. On A Parent Case Record the following fields should appear on the highlight panel a. Case Number a. Account Name b. Case Origin c. Created Date e.Priority f.Case Owner h.Case Type --------------------------------------- 1. On A Child Case Record the following fields should appear on the highlight panel a. Case Number a. Account Name b. Parent Case Number c. Created Date e.Priority f.Case Owner h.Case Type | Sprint 1 | 3 |  |  | Need Client Input Can we include the parent case on the child record high light pannel Subject instead of case type or orgin |  |  |  | Lalitha | Dev Completed
|  |  | Request Intake | As a Help Center Agent I need a Path Lifecycle on a case record for the parent and Child Chase | Given that I am a help center agent I should have a Path lifecylce with Chevrons for the following Statues: 1. New 2. In Progress 3. Pending 4. Closed | Sprint 1 | 3 |  |  |  |  | Dev Team Notes: Status values for Parent and Child Cases need to finalized |  | Aishwarya | Dev Completed
| Service Catalog |  | Request Intake | As Help Center Agent I should have a Parent Case Page that captures so information so that child cases can be captured | Given that I am a help center agent I should have a Parent Case that captures the following information | Sprint 1 |  |  |  | Need Client Input
| Service Catalog |  | Request Intake | As a Help Center Agent I need have a lightning page with specific components | Given that I am a help center agent I should have a Lighting Page with the following Components a. Tasks b. Activity c. Chatter Feed / Case Feed d. Email Component e. Related Contact | Sprint 1 | 3 |  |  |  |  | Dev Team Notes : Need to check the chatter post not showing up on the page |  | Sahana | Dev Completed
| Service Catalog |  | Service Catalog | As a Help Center Agent I need be able access the Service Catalog from a contact record so that I can link a case to Case directly | Given that I am a Help Center agent I should be able to do the following 1. Have a link or button I can click on an Contact record to access the service catalog 2. Select an item while on a existing Contact record 3. Have parent and child cases appear on theContact in a case history tab | Backlog | 5 | STR-010 |  | STORY Not needed |  | Do we want a button or link on the Contact Page? Should it be on a related list? What Fields should we have displayed in the case history tab? | David | Sahana | Cancelled
| Package Clean-Up |  |  | I need to be able to have a package clean up | Package Clean Up | Sprint 2
STR-SP3-001 | Service Catalog |  | IVR Reset | As a System I need to call Genie Mock Service to generate a Temporary IVR pin when a IVR Pin reset is initiated. | Given that I am a help Center agent I should have the following 1. When a password reset is initiated, the system should call the Mock Service via generate a temporary IVR PIn. 2. The Mock Service should generate a temporary password that meets the Pin complexity requirements | Sprint 3 | 5 | [5 empty] | David | Sahana | Ready for re-test | QA Pass retest done
STR-SP3-002 | Request Intake |  | Password Reset | As a System I need to call Genie Mock Service to generate a Temporary Password when a password reset is initiated. | Given that I am a help Center agent I should have the following 1. When a password reset is initiated, the system should call the Mock Service via API to generate a temporary password. 2. The Mock Service should generate a temporary password that meets the predefined password complexity requirements. | Sprint 3 | 3 | [5 empty] | David | Sahana | Ready for re-test | QA Pass retest done
| Service Catalog |  |  | I need to be able to have all Service Catalog Items built out so that I can access all service requests for a case | Given that i am a help center agent I need to have access to the following Service Catalog Items 1. Create all Categories from the Service Catalog 2. Create the issue type/Agent action for each Category in the catalog | Sprint 2 | 5 | [6 empty] | Lalitha | Dev Completed | QA In progress
| Account Mangement |  | Account Update | As a Help Center Agent I need to be able to access a flow that iniates an Account Update for an authenticated user so that they can Update their account details | Given that i am a help center agent I need to have the following 1. Account information Section a. Account Name b. Account Number c. Account Type d. Tier Level e. Account Address f. Primary Phone g. Email Address 2. Account Comments a. Comments - Free Text Field (Text Area) | Sprint 2 | 3 | [6 empty] | Lalitha | Dev Completed | QA Pass re-test done | Re-test
| Account Mangement |  | Account Update | UX Placeholder for Account Update | UX Placeholder |  | 1
| Account Mangement |  | Addres Change | As a Help Center Agent I need to be able to access a flow that initates a Address change so that a user can change their address in the system | Given that i am a help center agent I need to have the following 1. Account Information Section a. Account Name b. Account Number c. Account Type d. Tier Level e. Account Address f. Primary Phone g. Email Address 2. Address Change Section a. Comments - Text Area | Sprint 2 | 3 | [6 empty] | Lalitha | Dev Completed | QA Pass Re-test done | Re-test
| Account Mangement |  | Address Change | UX Placeholder for Address Change | UX Placeholder | Sprint 2 | 1 | [6 empty] | Nitish | UX Completed | QA Pass | story has been updated
| Account Mangement |  | Due To Death Issue | As a Help Center Agent I need to be able to access a flow that performs Due to Death issue | Given that i am a help center agent I need to have the following 1. Account Information Section a. Account Name b. Account Number c. Account Type d. Tier Level e. Account Address f. Primary Phone g. Email Address 2. Due to Death Issue Comments a. Comments - Text Field | Sprint 2 | 3 |  |  | May be customer validation model |  |  |  | Aishwarya | Dev Completed | QA Pass
| Account Mangement |  | Due To Death Issue | UX Placeholder for Due to Death Issue | UX Placeholder | Sprint 2 | 1 | [6 empty] | Nitish | Dev Completed | QA Pass
| Account Mangement |  | Missing Info Ap | As a Help Center Agent I need to be able to access to a flow that performs Missing Info - App | Given that i am a help center agent I need to have the following Given that i am a help center agent I need to have the following 1. Account Information Section a. Account Name b. Account Number c. Account Type d. Tier Level e. Account Address f. Primary Phone g. Email Address 2. Missing Info Comments a. Comments - Text Field | Sprint 2 | 3 | [6 empty] | Aishwarya | Dev Completed | QA Pass
| Account Mangement |  | Missing Info App | UX Placeholder for Missing info-App | UX Placeholder | Sprint 2 | 1 | [6 empty] | Nitish | Dev Completed | QA Pass
| Internal Demo Feedback |  | Recommendations Section |  | Given that i am a help center agent I need to have the following OOTB functionality from FF package • Recommendations on left side section in Home Page When the Help center agent click on "Recommendations" , on right side differ
STR-SP3-003 | Request Intake |  | Password Reset | As A Help Center Agent The Customer User Name should be Read Only in the Password reset Flow | Given that I am a help center agent 1. The Customer User name should be Read only for Password Reset 2. User name should be pulled from Login Object | Sprint 3 | 3 |  |  | need more information - Which login should we pull if |  |  | Vishnu | Vishnu | Dev Completed Ready for QA Testing | QA Pass
STR-SP3-004 | Request Intake |  | IVR Pin Reset | As A Help Center Agent The Customer User Name should be Read Only in the IVR Pin Flow | Given that I am a help center agent I should have the following 1. The Customer User name should be Read only for IVR Pin 2. User name should be pulled from Login Object | Sprint 3 | 3 | [5 empty] | Vishnu | Vishnu | Dev Completed Ready for QA Testing | QA Pass
STR-SP3-005 | Request Intake |  | Request Intake | As a Help Center Agent once a child case closes on a parent case the Save/Finish button should be greyed out | Given that I am a help center agent I should have the following 1. Once a case is set to status of "Closed" the Save Button is greyed out 2. Once a case is set to Status of "Closed" the finish button is greyed out 3. Once case is set to Status of "Closed" Process button is greyed out | Sprint 3 | 3 | [6 empty] | Dinesh | Dev Completed Ready for QA Testing | QA Pass
STR-SP3-006 | Request Intake |  | Request Intake | As a Help Center Agent once a parent case is closes there should no longer be an option to add a child case so that no child cases can be added | Given that I am a help center agent should have the following 1. Restriction on adding child cases once a parent case is set to closed 2. No Child case is able to be added once parent status is "Closed" | Sprint 3 | 5 | [5 empty] | David | Sahana | Dev Completed Ready for QA Testing | QA Pass retest done
| Service Catalog |  | Service Catalog | As a Help Center Agent I need to be able to have sub categories in the catalog so that agent actions are categorized | Given that I am a help center agent 1. Sub Categories in Account Managment section for the flows 2. Sub categories should be organized alphabetically within a category | Sprint 4 | 3 | [5 empty] | Lalitha | Lalitha | Pending for Client conformation - May need to move to Sprint 4
STR-SP3-007 | Deployment |  | Deployment Placeholder | Deploy to MS Enviornment | Deployment into MS Environment - Test | Sprint 3 | 5
STR-SP3-008 |  |  |  | As a Help Center Agent I need to be able to access a flow that performs ACH Restriction | Given that i am a help center agent I need to have the following Account/Login Information 1. Account Number (Number) Read Only 2. Log in Name (text) Check ACH Restriction Section with the following Fields: 3. Account Number (Read only) 4. Instant BP Allowed (Checkbox) 5. Reason (Text) | Sprint 3 | 3 |  |  | If Fields are Read-Only we should add tablev of the fields exist on financial account. If not we will use regular fields and section |  |  | Aishwarya | Aishwarya | Dev Completedd Ready fo QA | QA Pass retest done
STR-SP3-009 |  |  |  | As a Help Center Agent I need to be able to access a flow that performs TOA Research Request | Given that i am a help center agent I need to have the following 1. Section with the following READ ONLY Fields: Account information Section a. Account Name b. Account Number c. Account Type d. Tier Level e. Account Address f. Primary Phone g. Email Address Check ACH Restriction Section with the following Fields: 1. Is this Full Transfer (Checkbox) 2. Contra-firm Name (Text) 3. Contra- Account Number 3. Date of Transfer (Date) 4. Inquiry Type (Picklist) - Need choices 5. Transfer Type (Picklist) - Need Choices Comments 1. Comments | Sprint 3 | 3 | [5 empty] | Lalitha | Lalitha | dev completed ready for QA | QA Pass retest done
|  |  | Iframe | iFrame story Placeholder | Iform Placeholder story - Need details from client | Sprint 4
STR-SP3-010 | System |  | Sysem | As a Help Center Agent the Created By Field should have a hyperlink to a user record so that I can see who created a record | Given that I am a Help Center Agent I should have the following 1. A hyperlink on "Created by" field on all cases to a user story 2. Field should be automatically popualated upon created 3. Filed should not be editable in the list view | Sprint 3 | 3 | [5 empty] | Dinesh | Dinesh | Dev Completed Ready for QA Testing | QA Pass
STR-SP3-011 | System |  | App | I need to move Financial Flows from Service Console to Agent Desktop App | Story to deploy Financial Flows into Agent Desktop App | Sprint 3 | 3 | [8 empty] | QA Pass
Note on B2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: FF shouldn't be the feature. Let's split into three features: Service Catalog, Request Intake, and Agent Workflows
Note on D2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Let's have stories for (1) the ability to search for these (and specify how the search works; # chars required for the search, live vs. pressing enter, etc.), (2) when the action is clicked it shows in the catalog on left side and is highlighted, and (3) when user clicks submit the cases are created for the select actions and the appropriate request intake form appears
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Jordan Kunz (US)
Note on E9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Jordan Kunz (US) Reply: Let's also have a story for the ability to do this from parent case. Reply: Done @Jordan Kunz (US)
Note on D13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Let's add another story for the ability to retrieve the temp password from Genie service when user clicks the appropriate button. Add another story doing the same for IVR PIN reset
Note on E13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Jordan Kunz (US) Reply: If we're not doing any check that a user is authenticated, let's remove that from the description
Note on F13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Let's keep the ability to add something to the shopping cart and the actual workflow separate Reply: Let's specify what the click through is like; what do we click on parent case to initiate, what appears on the screen, what user enters, etc.
Note on K13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @David Hodges (US) Draft a success Message for Password reset flow
Note on E15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @David Hodges (US) Let's run a spellcheck. Seeing a number of typos
Note on F18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @David Hodges (US) For system related stories,, can we write ACs in way so that Testing team can follow and test accordingly
Note on E35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Jordan Kunz (US) Reply: Let's also have a story for the ability to do this from parent case. Reply: Done @Jordan Kunz (US)
Note on F51: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Pavan Behara (US) @Dinesh Kumar Rajendran (US) Updated with 3rd Criteria of acceptance
Note on G53: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @David Hodges (US) @Pallavi Raj (US) Please provide the Sub Categories for each Issue type

## Sprint 4
Story No | Menu | Story Name | Request Name | Story Name | User Story | Acceptance Criteria | Sprint Number | Story Points | Story ID | Priority | Notes | Approved by Client? | Questions | Owner | Developer | Dev Status | QA Status | Is it require Custimization
STR-SP4-001 |  |  |  | Subcategories for All Issue Types | As a Help Center Agent I need to sub categories Have Subcategories |  | Sprint 5 | 5 | [5 empty] | Pallavi | Lalitha | Pennding for Sub-Category Mapping
STR-SP4-002 | Service Catalog | Iframe | Service Catalog | Service Catalog Sub Categories - Account Managment | As a Help Center Agent I need to be able to have sub categories in the Account Management section in the Service catalog so that agent actions are categorized | Given that I am a help center agent 1. Sub Categories in Account Managment section for the flows 2. Sub categories should be organized alphabetically within a category 3. Only subcategory currently used is Request in Account MGMT Account Mgmt Account Link/Delink Account Restriction Assign a Customer Change My Info Cust SMS Status Electronic Documents ID Verfification Legal Entity Login Maintainence Merge Corp Svcs Acct OLA Reprint Original Acct Registration Info MDA Customer Responses Password Reset Security Options Simultaneuous Sessions Subscription Center Freeze/Unfreeze Core Accounts Data Central Disable Cash Management for CORE Portfolios User Profile Subcategory Requests 10b5-1 Enroll/Update Requests Account Closure Request Account Update Due to Death Issue Estate Conversion Information Verification Margin Upgrade Missing Info - App OFAC Country Access Restriction Removal Request OFAC Country Access Restriction Request Option Upgrade Reopen Account Request Research - Application Restricted Account/Deposit Update/Terminate Managed Products Pledged Account Update Sub Category Account Management Category Account Change - Account Closure Request Account Change - Account Update Account Change - Address Change Account Change - Mail Status Update Request Account Change - Margin Upgrade Account Change - Title Change Enable/Disable - 10b5-1 Enroll/Update Requests Enable/Disable - Disable Cash Management for CORE Portfolios Enable/Disable - Enable/Disable RTAO Flag Enable/Disable - Enroll/Update Managed Portfolios New Request - New Change Request New Request New Account Request - Bank New Request - New Account Request - Brokerage New Request - New Account Request - Futures New Request - Signature Card Request Others - Due to Death Issue Others Batch and Entry Code Change Request Others - Estate Conversion Others Information Verification Others - Missing Info - App Others - OFAC Country White List Exception Others - Option Others - Pledged Account Update Others - Research: Application Others - Restricted Account/Deposit Others - Update/Terminate Managed Products Others - Account Restriction Password/IVR Reset - Password Reset Password/IVR Reset - IVR pin Reopen Request Reopen Account Request stock plan Stock Plan Account Creation stock plan Stock Plan Activation Request | Sprint 4 | 3 | [5 empty] | David | Lalitha | Dev Completed Ready for QA | QA Pass
STR-SP4-003 | Service Catalog | Request Intake | Service Catalog | Bill Pay Add Funding Account Request Flow | As a Help Center Agent I need to have a Financial Flow for Bill Pay Add Funding Account | Given that i am a help center agent I need to have the following 1. Section with the following READ ONLY Fields: Account information Section a. Account Name b. Account Number c. Account Type d. Tier Level e. Account Address f. Primary Phone g. Email Address Bill Pay Add Funding Account Section with the following Fields: 1. Request Type - Bill Pay Add Funding Account 2. Accounts To Add: (Account number from above 3. Read only Text that reads: " All withdrawals from your Complete IRA, Including check writing, bill pay and the use of a VISA debit card, will be considered distributions and reportable on Form 1099-R. You must include all amounts you receive from the IRA in your gross income except amounts attributable to non-deductible contributions and amounts rolled back into an IRA or Qualified plan. Federal and state income tax will not be witheld from these payments and it is your responsibility for any adverse consequences that may arise from an IRA withdrawal and agree that E*TRADE Securities shall in no way be held responsible." 4. Check Box Field: Check this box when you have read the above to the customer | Sprint 4 | 5 | [5 empty] | David | Lalitha | Dev Completed Ready for QA | QA Pass - Read only Text alignment needs to be fixed by dev
STR-SP4-004 | Service Catalog | Request Intake | Service Catalog | Bill Pay Add Funding Account Request Flow - UX Design | I Need to have UX Design for Bill Pay Add Funding Account Request Flow - UX | UX Design Figma File for Bill Pay Add Funding Account Request | Sprint 4 | 1 |  |  | https://www.figma.com/file/pUAxgTURyqpGYekwxTUrxr/Morgan-Stanley-Flow%3A-Bill-Pay-Add-Funding-Account-Request?type=design&node-id=0%3A1&mode=design&t=Di7AHZdLVtz9Yo4C-1 |  |  | Pallavi | Nithish | Completed
STR-SP4-005 | Service Catalog | Request Intake | Service Catalog | Cash Mgmt Upgrade Request Flow | As a Help Center Agent I need to have Cash Mgmt Upgrade Request Financial Flow | Given that i am a help center agent I need to have the following 1. Section with the following READ ONLY Fields: Account information Section a. Account Name b. Account Number c. Account Type d. Tier Level e. Account Address f. Primary Phone g. Email Address 2. Cash Management Upgrade Request section with following fields 1. Checkbook(Checkbox) 2. Debit Card (Checkbox) 3. Alert Me(Checkbox) Buttons - (Dismiss , Save, Finish) Preview,Reset,Cancel | Sprint 4 | 3 | [5 empty] | David | Lalitha | Dev Completed Ready for QA | QA Pass
STR-SP4-006 | Service Catalog | Request Intake | Service Catalog | Cash Mgmt Upgrade Request - UX Design | I Need to have UX Design for Cash Mgmt Upgrade Request - UX Design | UX | Sprint 4 | 1 |  |  | https://www.figma.com/file/aqDptpAD4KRebBOyB87Ca3/Morgan-Stanley-Flow%3A-Cash-Management-Upgrade-Request?type=design&node-id=1%3A1174&mode=design&t=xRB6txW7ZFomqMPU-1 |  |  | Pallavi | Nithish | Completed | Wireframe is displaying Submit button instead of Finish on Cash Mgmt Upgrade Request page
STR-SP4-007 | Service Catalog | Request Intake | Service Catalog | Deposit Research: Check Flow | As a Help Center Agent I need to have a Deposit Research: Check Flow Financial Flow | Given that i am a help center agent I need to have the following 1. Section with the following READ ONLY Fields: Account information Section a. Account Name b. Account Number c. Account Type d. Tier Level e. Account Address f. Primary Phone g. Email Address 2.Check Flow section with following fields 1. Deposit Error (Picklist with values - Missing Check, Incorrect Account, Incorrect Amount) 2. Check Date (Date) 3. Check Number(Input text) 3. Check Amount(Number) 4. Check Bank Account(Input text) 5. Bank ABA(Input text) 6. Check Cashed(Boolean - Yes/No) 7.Initial deposit(Boolean - Yes/No) 8.Amount Posted(Number) 9.Correct Amount(Number) 10.Correct Account 11.Fund Deposited in Account 12. Comments | Sprint 4 | 5 | [5 empty] | David | Lalitha | Dev Completed Ready for QA-Ready for Retest | QA Pass
STR-SP4-008 | Service Catalog | Request Intake | Service Catalog | Deposit Research - Check Flow - UX Design | I Need to have UX Design for Deposit Research - Check Flow - UX Design | UX Design Figma File for Deposit Research - Check Flow - UX Design | Sprint 4 | 2 |  |  | https://www.figma.com/file/jubsxyCzzeM8fx6bCQccVE/Morgan-Stanley-Flow%3A-Deposit-Research%3A-Check?type=design&node-id=0%3A1&mode=design&t=NxXWt0aHqLg8APUd-1 |  |  | Pallavi | Nitish | Completed | Wireframe is displaying Submit button instead of Finish on Deposit Research:Check page | Ignore the Submit button on the Wirefram
STR-SP4-009 | Service Catalog | Request Intake | Service Catalog | Deposit Research: Wire Request | As a Help Center Agent I Need to have a Deposit Research:Wire Request Financial Flow | Given that i am a help center agent I need to have the following 1. Section with the following READ ONLY Fields: Account information Section a. Account Name b. Account Number c. Account Type d. Tier Level e. Account Address f. Primary Phone g. Email Address Wire Request section with following fields 1.Wire Amount(Number) 2. Currency- Need Choices 3. Wire Date (Date) 4.Bank ABA(Input text) 5. Foreign Bank( Boolean - Yes/No) Deposit Research Wire Request Comments : Section 1. Comments 7. Alert Me (checkbox) | Sprint 4 | 5 | [5 empty] | David | Lalitha | DEV Completed Ready for QA | QA Pass
STR-SP4-010 | Service Catalog | Request Intake | Service Catalog | Deposit Research - Wire Request - UX Design | I Need to have UX Design for Deposit Research - Wire Request - UX Design | UX Design Figma File for Deposit Research - Wire Request - UX Design | Sprint 4 | 1 |  |  | https://www.figma.com/file/g4inB0IHYKoyHIs9bfXrnY/Morgan-Stanley-Flow%3A-Deposit-Research---Wire-Request?type=design&node-id=0%3A1&mode=design&t=a8UeRrPoSQMld2cp-1 |  |  | Pallavi | Nitish | Completed | Wireframe is displaying Submit button instead of Finish on Deposit Research:Wire page
STR-SP4-011 | Service Catalog | Request Intake | Service Catalog | UX Design Feedback Updates | UX Design Feedback updates from MS |  | Sprint 5 | [6 empty] | David | Nitish | Pending for Feedback Figma Document
STR-SP4-012 | Password Reset | Password Reset | Service Catalog | Passwor Reset Login Name | As a Help Center Agent, On the Password Rest form , i Ishould able to see web login name instead of login id | 1. Web Login Field on Passwor Reset Flow On the Password Rest and IVR pin Dynamic intake form . Agent should see the Web Login Name instead of User ID. Web login should flow from Login record name | Sprint 4 | 5 | [5 empty] | David | Sahana | Dev Completed , ready for QA | QA Pass
STR-SP4-013 | Password Reset | Password Reset | Service Catalog | Disable Continue Button on a closed case | As a Help Center Agent I should be able to have the continue button disabled not able to make call to the web service when a case is closed | 1. Continue button disabled / greyed out when a case is closed 2. No Ability to make call to Web Service | Sprint 4 | 5 | [5 empty] | David | Sahana | Dev Completed , ready for QA | QA Pass
STR-SP4-014 |  | Deployment | Deployment to Client Brnach |  | Deployment to Client Brnach | Deployment to Client Branch | Sprint 4 | 3 | [5 empty] | David | Dinesh | Dev Completed
STR-SP4-015 |  | Deployment | Fixing Deployement Error |  | Fixing Deployement Error | Fixing Deployement Error | Sprint 4 | 3 | [5 empty] | David | Sahana | Dev Completed
STR-SP4-016 |  | Deployment | Helping Client for Smoke Testing |  | Helping Client for Smoke Testing | Helping Client for Smoke Testing | Sprint 4 | 3 | [5 empty] | David | Vishnu | Dev Completed
STR-SP4-017 | Service Catalog | Deployment | Service Catalog | Update service Catalog verbiage | Verbiage should reade "Please select one or more requests / inquiries below and click Create to process the requests | Verbiage should reade "Please select one or more requests / inquiries below and click Create to process the requests | Sprint 5 | 1
STR-SP4-018 | Service Catalog | Deployment |  | Update service Catalog verbiage | Add Subject Parent Case | Subject added to Parent Case Case Component | Sprint 5 | 1
Research ATM
Research ATM UX
Research Bill Pay
Research Bill Pay UX
Withdrawl Reseach: ACH
Withdrawl Research: ACH UX
Withdrawl Research: Check
Withdrawl Research: Check
Dividend Research
Dividend Research UX
Note on Q3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Pallavi Raj (US) @David Hodges (US) Can we do sub-category mapping internally and we can review on our call
Note on H4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @David Hodges (US) @Pallavi Raj (US) Please provide the Sub Categories for each Issue type
Note on F7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Pallavi Raj (US) Can you check the AC Reply: @Dinesh Kumar Rajendran (US) updated
Note on N7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Pallavi Raj (US) Can you check the AC Reply: @Dinesh Kumar Rajendran (US) Updated
Note on F9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @David Hodges (US) We need more details for this flow
Note on G9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Pallavi Raj (US) @David Hodges (US) Can you get the picklist value for 10.Correct Account 11.Fund Deposited in Account for now team has given Yes/no as picklist value
Note on I10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Pallavi Raj (US) / @David Hodges (US) : I have updated the story point from 1 to 2 as this flow design has more screens.
Note on F11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Pallavi Raj (US) Can you check the AC Reply: @Dinesh Kumar Rajendran (US) updated @David Hodges (US) we need more details here
Note on G11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: Hi @David Hodges (US) , do we need "Alert Me" checkbox? I remember we discussed of not having this checkbox in any flow. Thanks. cc @Pallavi Raj (US)
Note on Q13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @David Hodges (US) @Pallavi Raj (US) , Nitish has mentioned this story required a figma document , can you get it from client

## Sprint 5
Menu | Feature | Request Name | User Story | Acceptance Criteria | Sprint Number | Story Points | Story ID | Priority | Notes | Approved by Client? | Questions | Owner | Developer | Dev Status | QA Status | Is it require Custimization
Service Catalog |  | Service Catalog | As a Help Center Agent I should be able to Access Service Catalog After Clicking Validate on the customer validation module | Given that I am a Help Center agent I should be able to do the following 1. Access to the Customer Validation Module 2. "Validate" button within the Customer Validation Module that is visible and accesible 3. Be redirected the Service Catalog after a successful validation | Backlog TBD |  | STR-002 |  | Not doing this sprint
Service Catalog |  | Service Catalog | Update service Catalog verbiage | Verbiage should reade "Please select one or more requests / inquiries below and click Create to process the requests |  | 1
Service Catalog | Iframe | Iframe | iFrame Flow - Wire | iFrame story Placeholder - Wire | Iform Placeholder story - Need details from client | Sprint 4 | 8 | [5 empty] | David | Sahana | Pending for IFrame Script and access on our Dev Org
|  |  | Overview Section Each Flow | Overview each flow
|  |  | to |  | ¦
|  |  | Dividend Research | As a Help Center Agent I need to be able to have a financial flow for Dividend Research So that I can enter relevant information for a customer case Given that I am a Help Center Agent I should have the following available: Section with the following Fields: Account information Section a. Account Name b. Account Number c. Account Type d. Tier Level e. Account Address f. Primary Phone g. Email Address Dividend Research a. Inquiry Type (Picklist: DRIP Research, General Dividend Research, Optional Dividend Research, Bond Interest Research) REQ b. Symbol or Cusip (Text) REQ c. Company Name (Text) REQ d. Dividend Amount (Currency) - Displays if DRIP Research or General is selected REQ e. Dividend Pay Date (Date) - Displays if DRIP Research or General is selected REQ f. Share Amount (Currency) - Displays if Optional or Bond is selected REQ g. Coupon Rate - Displays if BOND Interest is Selected h. Coupon Pay Date - Displays if BOND Interest is Selected J. Maturity Date - Displays if BOND Interest is Selected
\
Note on P5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Pallavi Raj (US) @David Hodges (US) We still didn't get access to Ifram Script and dev Org access. Can you talk to client and get the access ASP.

## Form-WorkBook
Form | Service Type | Field Name | Data Type | Section Name | Is ReadOnly | Is Reportable | Is Required
SP4-Form_1 | Cash Mgmt Upgrade Request Financial Flow | Account Name | Text | Account information Section | Yes | Yes | Yes
|  | Account Number | Text | Account information Section | Yes
|  | Account Type | Picklist | Account information Section | Yes
|  | Tier Level | Picklist | Account information Section | Yes
|  | Account Address | TextArea | Account information Section | Yes
|  | Primary Phone | Phone | Account information Section | Yes
|  | Email Address | Email | Account information Section | Yes
|  | Checkbook( | Checkbox) | Cash Management Upgrade Requests | No
|  | Debit Card | (Checkbox) | Cash Management Upgrade Requests | No
|  | Alert Me | (Checkbox) | Cash Management Upgrade Requests | No
SP4-Form_2 | Deposit Research: Check Flow Financial Flow | Account Name |  | Account information Section | Yes | yes
|  | Account Number |  | Account information Section | Yes
|  | Account Type |  | Account information Section | Yes
|  | Tier Level |  | Account information Section | Yes
|  | Account Address |  | Account information Section | Yes
|  | Primary Phone |  | Account information Section | Yes
|  | Email Address |  | Account information Section | Yes
|  | Deposit Error (Picklist with values - Missing Check, Incorrect Account, Incorrect Amount) |  | Check Flow | No
|  | Check Date (Date) |  | Check Flow | No
|  | Check Number(Input text) |  | Check Flow | No
|  | Check Amount(Number) |  | Check Flow | No
|  | Check Bank Account(Input text) |  | Check Flow | No
|  | Bank ABA(Input text) |  | Check Flow | No
|  | Check Cashed(Boolean - Yes/No) |  | Check Flow | No
|  | Initial deposit(Boolean - Yes/No) |  | Check Flow | No
|  | Amount Posted(Number) |  | Check Flow | No
|  | Correct Amount(Number) |  | Check Flow | No
|  | Correct Account |  | Check Flow | No
|  | Fund Deposited in Account |  | Check Flow | No
|  | Comments |  | Check Flow | No
SP4-Form_3 | Deposit Research:Wire Request | Account Name |  | Account information | Yes
|  | Account Number |  | Account information | Yes
|  | Account Type |  | Account information | Yes
|  | Tier Level |  | Account information | Yes
|  | Account Address |  | Account information | Yes
|  | Primary Phone |  | Account information | Yes
|  | Email Address |  | Account information | Yes
|  | Wire Amount(Number) |  | Wire Request | No
|  | Currency- Need Choices |  | Wire Request | No
|  | Wire Date (Date) |  | Wire Request | No
|  | Bank ABA(Input text) |  | Wire Request | No
|  | Foreign Bank( Boolean - Yes/No) |  | Wire Request | No
|  | Comments |  | Deposit Research Wire Request Comments | No
SP4-Form_4